## Current Iteration
|  | Iteration Number: |  |  |  | 2
|  | Expected Total effort: |  |  |  | 36
|  | Days In Sprint: |  |  |  | 14
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Fix Multiplayer – Evan | 25 | Days (Points Completed) 1: 20 | 5 | 80%
Clean Code – Mcclain | 3 | Days (Points Completed) 1: 3 | 0 | 100%
0
0
0
options menu – John | 2 | Days (Points Completed) 1: 2 | 0 | 100%
Arcade Plans – Tyler | 4 | Days (Points Completed) 1: 4 | 0 | 100%
0
0
0
Pause button – Cougar | 2 | Days (Points Completed) 1: 2 | 0 | 100%
Feature 12 | [21 empty] | 0
Feature 13 | [21 empty] | 0
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 36 | 5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 86.11%
Ideal Trend | 36 | 33.4286 | 30.8571 | 28.2857 | 25.7143 | 23.1429 | 20.5714 | 18 | 15.4286 | 12.8571 | 10.2857 | 7.7143 | 5.1429 | 2.5714 | 0 | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days