## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 388
|  | Days In Sprint: |  |  |  | 14
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Finish Multiplayer | 20 | [20 empty] | 20 | 0%
Clean up Lobby | 5 | [20 empty] | 5 | 0%
Pause Button | 5 | [20 empty] | 5 | 0%
begin Arcade | 15 | [20 empty] | 15 | 0%
Powerups | 5 | [20 empty] | 5 | 0%
Arcade menu option | 2 | [20 empty] | 2 | 0%
Git gud | 336 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | [6 empty] | 0 | 100%
Feature 8 | [21 empty] | 0
Feature 9 | [21 empty] | 0
Feature 10 | [21 empty] | 0
Feature 11 | [21 empty] | 0
Feature 12 | [21 empty] | 0
Feature 13 | [21 empty] | 0
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 388 | 364 | 340 | 316 | 292 | 268 | 244 | 220 | 196 | 172 | 148 | 124 | 100 | 76 | 52 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 52 | 86.6%
Ideal Trend | 388 | 360.2857 | 332.5714 | 304.8571 | 277.1429 | 249.4286 | 221.7143 | 194 | 166.2857 | 138.5714 | 110.8571 | 83.1429 | 55.4286 | 27.7143 | 0 | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days