## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 19
Days In Sprint:
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
arcade events – Tyler | 8 | Days (Points Completed) 1: 3; Days (Points Completed) 2: 3; Days (Points Completed) 3: 2 | 0 | 100%
arcade ball – Evan | 2 | Days (Points Completed) 2: 2 | 0 | 100%
Maps – McClain | 2 | Days (Points Completed) 4: 2 | 0 | 100%
Activation – Cougar | 3 | Days (Points Completed) 3: 3 | 0 | 100%
Settings – John | 4 | Days (Points Completed) 1: 2; Days (Points Completed) 4: 2 | 0 | 100%
0
Feature 7 | [21 empty] | 0
Feature 8 | [21 empty] | 0
Feature 9 | [21 empty] | 0
Feature 10 | [21 empty] | 0
Feature 11 | [21 empty] | 0
Feature 12 | [21 empty] | 0
Feature 13 | [21 empty] | 0
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 19 | 14 | 9 | 4 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 100%
Ideal Trend | 19 | 18.05 | 17.1 | 16.15 | 15.2 | 14.25 | 13.3 | 12.35 | 11.4 | 10.45 | 9.5 | 8.55 | 7.6 | 6.65 | 5.7 | 4.75 | 3.8 | 2.85 | 1.9 | 0.95 | 6.8834e-15
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days